## Rogers
報告先 | [9 empty] | 報告 2016年 10月 29日
アンソニー常務 |  |  |  | 出張計画 及び 出張報告書
作成：佐々木
写し配付先
小川MD, 宇土GM |  |  |  | 対応 | アンソニー常務 |  |  |  | 期間 | 2016-10-27
森M, 松本GM |  |  |  |  | 小川ＭＤ
佐藤M |  |  |  |  | ドミートリィ、佐々木 |  |  |  | 添付資料 |  | 有 | 無
相手先 | [5 empty] | 相手先 面談者 |  | Mr.Timo（購買）, Mr.Rummens(営業)
|  |  | Rogeｒs |  |  |  |  | Mr.Sascha(技術), Mr.Legath(技術)
Mr,Bartl(品証）
目的
ZTA基板で発生した絶縁破壊不良に対するMWの対応
打ち合わせ内容
＜背景＞
車載メーカにて絶縁破壊不良が発生。Rogersの顧客(Infineon)でも絶縁破壊は検出されておらず、END顧客にて絶縁破壊が
発生。Rogersでは絶縁破壊試験を実施していなかった。
絶縁破壊が発生したﾊﾟﾜｰﾓｼﾞｭｰﾙは、1ユニットの中に3枚の基板が搭載されており、その内の1枚で絶縁破壊が発生。Rogers
曰くこのﾕﾆｯﾄ内の3枚の基板はMWの同一ロット基板であるとの事。以前Rogersより連絡のあった20μｍと80μmのボイドは絶縁
破壊の起きた本ﾕﾆｯﾄ内の残りの2枚の基板から検出されている。しかし、これら2つの確認されたボイドからは絶縁破壊は発生し
ておらず。
|  | ＜ﾊﾟﾜｰﾓｼﾞｭｰﾙ概略図＞ |  |  |  |  | ＜予想されるﾊﾟﾜｰﾓｼﾞｭｰﾙ製品＞
＜MARUWAの対応事項＞
・新規CP Filter対策品、またカメラ検査を実施したサンプルの提供（対策品と通常品双方の提供）・・・・・出荷日：11/17
※新規Filter納入日については11/4と客先に回答済み。
・上記対策品の効果確認を実施し、通常品との差異を調査結果にまとめ報告・・・・・回答日：11/17
ex. ラップ表面をSEM観察し、ボイドの分布図、発生率の相違を確認する。
・新規Filter仕様の量産化については、PCN(ZTA & Al2O3共に)を発行し客先へ提出・・・・・回答日：11/3
※ZTA(0.25t&0.32t)に加え、Al2O3についても新規Filterを使用し、量産化を図る。
・新規カメラシステムによる100%外観検査の対応可否を確認・・・・・回答日：11/14
・新規カメラシステムで検出されたボイド現品の客先への提供・・・・・出荷日：11/30
・ECNのProcedureの提供・・・・・回答日：10/28(提出済み）
・追加試験項目である貫通穴品のサンプル提供・・・・・出荷日：11/17
※穴径は0.10, 0.25 & 0.30mm狙い。各5枚x3種＝15枚のサンプル提供。破壊電圧測定結果についても併せて回答。
・追加試験項目であるピンホールサンプル対応可否の連絡・・・・・回答日：11/17
・クラックの進展と絶縁破壊強度との関連を調査する測定可否について連絡・・・・・回答日：11/4
＜その他回答事項＞
・新規カメラシステムの検査能力・・・7k枚/日 x 25日稼働 = 175k枚/月
・新規カメラシステムについは11/30までに設置完成予定であり、ZTA（0.32t）についてのみ検査対象とする。
・新規ホーニング機、反り直し炉については、2017年1月に設置完了
・新規測定設備(絶縁破壊測定機等）については、2017年3月に設置完了
・両社間の取交し（納入仕様書等）が曖昧なものがあるため、今回を機に再度取決めを行う事を要望
＜生産状況に関して＞
ZTA-0.32tについては在庫調整中であるが、ZTA-0.25tについては10k枚程度の追加注文が入る予定。
＜次回MM-Rogers電話会議日程＞
日時：11月2日（水）午後4時～(マレーシア時間）
必要回答事項・・・①上記調査項目のガントチャート
②ZTA基板納入仕様書案の提供日の連絡
意見/考え
上記多くの宿題事項が出たが、車載用製品であるため、早急に対応し本件の終息を図る。
絶縁破壊が発生
20μｍや80μmのボイドが確認されたものの絶縁破壊は起きておらず。

## 対応事項と期限
＜対応事項と期限＞
Nov 27th: Meeting with Maruwa about root cause analysis and counter measures
Maruwa: Mr. Anthony (CEO), Mr. Sasaki (Managing Engineering), Mr. Ogawa (Managing Director Sales), Mr. Fedorov (Sales)
Rogers: Ilker Sen (QA to customer), Timo Hartmann (Manager Purchasing), Thomas Bärtl (QA to supplier), Marc Rummens (Key Account Manager), Alexander Legath (Manager Engineering)
| Containment: New Filter system | New filter system will be installed at tape casting process to reduce risk of foreign particles. | open | 04. Nov 16 | MARUWA
|  | Maruwa to provide PCN; will be treated as minor change | open | 03. Nov 16 | MARUWA
|  | Provide analysis of pore size before and after installation of new filter system by lapping of ceramics | open | 17. Nov 16 | MARUWA
| Containment: Installation of camera system | Verification if camera system for 100% inspection. | open | 14. Nov 16 | MARUWA
|  | Implementation of camera system for 100% inspection for ZTA material. | open | 30. Nov 16 | MARUWA
|  | Maruwa to provide instruction of testing and picture about test setup | open | 30. Nov 16 | MARUWA
|  | Maruwa to provide samples which have been rejected by camera system to Rogers | open | 30. Nov 16 | MARUWA
|  | Maruwa to investigate reject samples by means of grinding and microscope inspection. | open | 17. Nov 16 | MARUWA
| Research about effect of bubbles | Produce samples with through hole diameters 0.1mm; 0.25mm; 0,3mm (made before and after sintering) | open | 17. Nov 16 | MARUWA
Samples to be sent to Rogers (5x) and to Maruwa Japan for Analysis by Nov 17th
|  | Check possibility to produce samples with on purpose bubbles by elimination of degassing after slurry mixing or other idea | open | 17. Nov 16 | MARUWA
|  | Investigate breakthrough voltage | open | 17. Nov 16 | MARUWA
|  | Provide samples (5pcs each of pin hole and through hole) of both types to Rogers for additional testing | open | 17. Nov 16 | MARUWA
|  | Check possibility of measureing breakdown voltage under mechanical load; if possible then investgation coul be done until 17th | open | 04. Nov 16 | MARUWA
| Others | Maruwa Malaysia is planning to extend the on-site capabilites of lab by additional machines for breakdkdown test, x-ray diffractometer, bending strength. Plan is Q1/2017. | Info | - | -
| Quality system at Maruwa | PCN: Three categories. | Info | - | -
A: Change of raw material --> PCN
B: Method of shipment, inspection method, process --> PCN
C: Minor internal changes in logistics, … --> no PCN
|  | Procedure to be sent to Rogers | open | 28. Okt 16 | MARUWA
| Specification | There is no agreed quality guideline between Maruwa Malayia and Rogers. | Info
|  | Maruwa to make proposal about specification and other necessary agreements. Timeline to be defined in follow-up-call at Nov 2nd. | open | tbd | MARUWA