## 18jun
FOOLOW up Activity
Department | Process | Discussion | Action | PIC | Status
ALN | Casting System | Casting System not implemented | Online meeting with Mr Ravi | Mr Siva | Done
|  | a. Data transfer error | a. Rectify the bug and test run on 19/jun | Mr Ravi | Done
|  | b. Report not generated | b. Programmer will work on once complete the data entry screen error | Ms Sudha | Will work on after completing the thickness data recording
| Raw Material System | Provide the source code for RM System & RMQC | Will develop the atcion plan | Mr Ravi | This will include the Raw Material system as well
| PC System | Requesting for PC system (WEB base) |  | Mr Siva | To assign the right project leader
| Recycle Label | To implement similar label system for recycle |  | Mr Siva | To further discuss with Mr Ono
Yudentai | QA System | Online meeting with Mr Kitauji |  | Mtr Siva | Done
1st Step
|  | Process list down - | Prepare the process list - Date TBC | Mr Takechi
Others |  | Wireless charger implementation for PLANT 6 |  | Mr Siva/Prem | Will check the market availability
Developing IT hub for India

## 19jun
Follow Up Activity
Department | Process | Discussion | Action | PIC | Status
ALN | Casting System | Casting System not implemented | Online meeting with Mr Ravi | Mr Siva | Done
|  | a. Data transfer error | a. Rectify the bug and test run on 19/jun | Mr Ravi | Done
|  | b. Report not generated | b. Programmer will work on once complete the data entry screen error | Ms Sudha | Will work on after completing the thickness data recording
Tokai | CV Mould | a. Tokai standard lead time | Std : 6 weeks | Tokai | This is with condition a. No changes in drawing b.
|  | b. Weekly delivery schedule update | Currently submitting but only to Japan Maruwa |  | Will add in Maruwa Malaysia members in loop
|  | c. Repair mould | Mould sending for repair should be group in same number | Mr Amry / Mr Siva | Mix up causing Tokai to spend time to segregate and need to uniform the design with the drawing
|  | d. Inspction report submission | Tokai will email the inspection report once the mould is shipped | Tokai | Report will be upload into MMS
|  | f. Cost Improvement | Tokai will propose alternative material for quality improvement Type of Material : G3 & G4 RFF 40 ~ 70 | Tokai
[6 empty] | COATING | SHIPMENT
WIRE CUT
EDM JIG
EDM PROCESS
CARBIDE BLOCK